## Sheet1
Professional Learning Outline Plan
|  |  | Organization/District | Lamar University Admission Team/BISD
|  |  | Date | Spring 2023-Fall 2023
| PHASE | DETAILS | EFFECTIVE PRINCIPLE | TASK OWNER | START DATE | DUE DATE | AUDIENCE | OBJECTIVE | COLLABORATION | RESOURCES | DIGITAL FILES | DIGITAL FILES | DIGITAL FILES | DIGITAL FILES | % OF TASK COMPLETE
DESCRIPTION
1 | Alternative PL Introduction -ePortfolio Implementation | * Meet w/Admin, share proposal letter & video *Send invite/google form for pilot committee *Presentation (Alternative PL) *1st EP Team meeting *3 Column Table/Schedule for the year |  | Project Facilitator Project Facilitator Project Facilitator Project Facilitator Project Facilitator | 7/4/2022 7/15/2022 7/18/2022 7/27/2022 8/3/2022 | 7/15/2022 7/29/2022 7/29/2022 8/5/2022 8/12/2022 | Admin/Teachers/PL Team Admin Admin Admin/Teachers PL Team | There will be a meeting with the administration team. The PL: Call to Action video will be presented. The admin and teachers will be given a survey to complete. | /NA | A laptop with a smart board in conference room. Also a solid internet connection. | https://docs.google.com/presentation/d/1MTdN0dC5K2AQ5L-KxwZJiu8Z-VZKNUxN_ESlFxlNbOo/edit?usp=sharing | https://www.youtube.com/watch?v=pxs4rNaU2r8&feature=emb_title
2 | Alternative PL -Portfolio Implementation Start with WHY | * What is the EP *Add Why/How *Update EP (Ongoing) |  | Project Facilitator Project Facilitator Project Facilitator Project Facilitator Admin Project Facilitator/Admin/Finance Project Facilitator/ PL Team | 8/5/2022 8/5/2022 9/7/2022 9/7/2022 10/10/2022 10/10/2022 11/2/2022 | 8/29/2022 8/29/2022 10/3/2022 10/3/2022 10/31/2022 10/31/2022 12/16/2022 | Admin/Grade Level Lead/Teachers Admin/Grade Level Lead/Teachers Admin/Grade Level Lead/Teachers Admin/Grade Level Lead/Teachers Teachers Finance PL Team/Teachers | A propsal will be hand delivered to the admin and emailed a pdf. The innovation media proposal will be presented. | The implementation plans and goals will be discussed. Futhermore, the team will have a disucssion about the budget for the innovative project. The devleoped and post-production of the professional learning will occur. | A laptop; a smart board; good wireless internet connection | https://docs.google.com/presentation/d/1MTdN0dC5K2AQ5L-KxwZJiu8Z-VZKNUxN_ESlFxlNbOo/edit?usp=sharing | https://www.youtube.com/watch?v=8JUQoY0-bTY | https://briankizzee.wordpress.com/61-2/concepts-of-educational-technology/edld-5305/
3 | PL Launch & Execituon - Professional Leanring sessions | PL Sessions (Asynchronus) Deliverables Teacher ePortfolios Feedback Forms | Duration/Engagment Modeling Modeling Specific Content | Project Facilitator/Teachers Project Facilitator Teachers Project Facilitator/Teachers | 1/10/2023 1/10/2023 1/10/2023 1/10/2023 | 3/10/2023 3/10/2023 3/10/2023 3/10/2023 | Teachers Teachers Teachers Teachers | The professional learning will start for the participants to build effective e-portfolios. Feedback forms will be given to the admin and teachers at the end of the PL sessions to provide feedback. | /NA | A laptop; a smart board; internet connection | https://docs.google.com/presentation/d/1MTdN0dC5K2AQ5L-KxwZJiu8Z-VZKNUxN_ESlFxlNbOo/edit?usp=sharing | https://forms.office.com/r/FupKg6rzTb | https://briankizzee.wordpress.com
4 | PL Performence & Control - Hold coaching sessions and monitor implementation | Develop Coaching Schedule/Goals Implement Coaching Schedule/Goals Deliverables | Specific Content Engagement/Support Modeling | Project Facilitator/Teachers Project Facilitator/Teachers Project Facilitator | 8/8/2023 8/8/2023 8/8/2023 | 10/31/2023 10/31/2023 10/31/2023 | Teachers Teachers Teachers | The team will be able to talk about new ideas for the development of effective coaching goals for the participants in the program. | The facilitator and teachers will develop and implement the coaching schedule and goals. | A laptop; a smart board; internet connection | https://docs.google.com/presentation/d/1MTdN0dC5K2AQ5L-KxwZJiu8Z-VZKNUxN_ESlFxlNbOo/edit?usp=sharing
5 | Feedback and Reflection - Celebrate success. | Feedback Forms Submit Credit Project Review Meeting/Celebration Reflect and Adjust | Engagement Duration Engagement Engagement | Project Facilitator Teachers/Admin/HR Project Facilitator/Admin/Teachers Project Facilitator/Admin | 5/17/2023 5/17/2023 5/17/2023 5/17/2023 | 5/26/2023 5/26/2023 5/26/2023 5/26/2023 | Teachers Admin/HR Admin/Teachers Everyone :) | The facilitator, admin, and teachers will be able to identify the success. | The PL will collaborate and disucss the next steps moving forward with the focus towards effective goals. | TBA | https://docs.google.com/presentation/d/1MTdN0dC5K2AQ5L-KxwZJiu8Z-VZKNUxN_ESlFxlNbOo/edit?usp=sharing